September 17, 2007

Progress since meeting with Mark and Joanne August 24th, 2007

- Alanine dipeptide with chiro-inositol
  - Simulations are completed and analyzed. Simulations of glycine dipeptide and isomers have also been analyzed. Need to quantify with errors, but at this point enough information for qualitative conclusion.
  - Did these results add anything new or change our current conclusions?

- Single chain (8 residue) GAGAGAGA peptide with 4 inositols to compare with the multichain systems. Start with scyllo.
  - Started simulations to run for 350 nanoseconds
  - Had a few technical errors
  - Currently script crashes on CCB, need to find out why and fix this problem (whether has to do with CCB new interactive job constraint)
  - Need to carefully think about questions we want to answer with this system

- Restrained sampling of the same single chain GAGA peptide system (currently running under stephanie's account)
  - Stephanie's jobs of this system have been done and she has about 350 ns of data. She has been doing analysis on this about a week ago. I'm not sure what were the results.
- Run stephanie's systems without inositol as control simulations
  - Stephanie has done GAGAGAGA 4 chained sheets in water for 100ns

- Since steph only ran systems with scyllo and since her systems have converged, we can pick 1 of her system to redo with epi, myo and chiro. It would be most meaningful to pick the 4 chain (sheet)
  - Need to do this
  - Take her 4 chain “sheet” GAGAGAGA and repeat with epi and myo with the same starting conditions, run script, etc.

As an aside, it will be very interesting to run simulations with the different isomers of inositol with the octane bilayer and see how the inositol partitions on the surface of the bilayer.

The Plan

Next Month: Now to October 17th, 2007
General goals:
- Get started with some beta sheet stability experiments (polyglutamine? charged side-chains)
- understand the various analysis that has been done for peptides and be able to make sure that you've duplicated the analysis stephanie has done
- extend the analysis for multipeptides(morphology, and multidentate analysis)
- figure out what analysis to be done for the single peptide system
- Finish the ion pair paper draft
- Perform some preliminary analysis of the P450cam system
- Decide what to present at my committee meeting: ion pair, preliminary results for P450cam, results for inositol + dipeptide, preliminary results for multi-peptide systems. Future works plans.
- Put together presentation, and report for committee meeting targeted for end of October.
- 5 hours of lecture/seminar time per week

Week of September 17, 2007
Set up and run the 4 chain GAGAGAGA sheet system with epi, myo and chiro (why am I using this system and not the monomeric peptide systems? why use 4 inositols instead of 2? should I run chiro as well?)
Find the following used by steph:
- Initial starting structure
- Placement of inositol isomers
- Topologies
- MD parameters for EM, equilibration and production dynamics
- Construct/modify chain_jobs.pl script to handle these systems (first find what is wrong with the script currently)
Construct peptide + inositol analysis program which does exactly what Stephanie's does.
  - Works for any number of peptides and any number of inositols in a system. Extensible for inter-strand, and intra-strand analyses as well.
  - Dependency analysis: code to read in system coordinates will need to be rewritten every time there are peptides of different length.
    - only need peptide backbone, inositol OH groups makes it sequence independent (do not need to consider side-chains) and stereochemically (orientation of OH groups axial vs equatorial) independent.
1. Extend analysis for the multipeptide systems
2. Figure out what analysis to be done for the single peptide system and do the analysis
3. Extend my p450cam simulations for another month
4. Put together a report for alanine and glycine dipeptide + inositol: motivation, methods, results (figures) and conclusions.
5. Readings to be done:
  - Medium: 1 BCH2021 paper (1)
  - Medium: Papers relating to stability of beta-sheets (2)
  - Easy: General amyloid, alzheimer's review and experimental/theory papers (5)
  - Difficult: Molecular dynamics Abeta, amyloid, aggregation papers (2)
  - Difficult: Statistical mechanics
Week of September 24, 2007 TBD

Week of October 1, 2007 TBD

Week of October 8th, 2007 TBD